## Sheet1
Schedule
Month | Year | Tasks & Events | Status | Details
9 | 38 | Topic suggestion, find sources | Done
| 39 | Meeting with supervisor, thesis plan, table of contents | Done
10 | 40 | Methods chapters
| 41 | Re-evaluate schedule, theoretical chapters
| 42 | Development continues at least to this point
| 43 | Implementation chapters
| 44 | Implementation chapters
11 | 45 | Release candidate |  | Optimistic schedule
| 46 | Schedule seminar |  | 90% of report required before seminar
| 47 | Conclusions chapters
| 48 | Seminar? |  | Depends on available timeslots
12 | 49 | Käsittelykokous |  | Finished thesis if writing around 2+ pages/day
| 50 | Peer evaluation, self-evaluation, language check, etc
51
| 52 | Release candidate |  | If not finished before
53
1 | 1
2
| 3 | Peer evaluation, self-evaluation, language check, etc |  | If not finished in 2018
| 4 | Initial deadline |  | Finished thesis if writing around 1+ pages/day
2 | 5
Contact Info: |  |  |  | Grade
Email |  | h8718@student.jamk.fi, markus.moilanen@protacon.com |  | 3 - 5
Phone |  | 0442582282